## MasterList
Sr No. | Server | Services | Application Type | Complexity | Rewrite/Upgrade | UpgradeAssistantServiceLog (Refere excelsheet Tabs) | Path | Start Date | End Date | Development Sprint | Comment | Postman Collection | Blocker's |  | Request | Response
1 | mobileapp | FHMA-Leviathan | API | Medium | Only C# Migration | FHMA | https://ccldev.visualstudio.com/Middleware/_git/carnival-server-dotnet | 2022-06-16 | 2022-07-01 | Last Sprint
2 |  | FHMA-Leviathan-configuration | API | Low | Only C# Migration | FHMA | https://ccldev.visualstudio.com/Middleware/_git/carnival-server-dotnet | 2022-06-16 | 2022-07-01 | Last Sprint
3 | web1a/1b | gangwayadmin | Asp.net MVC Web | High | C# + SP Migration |  | https://ccldev.visualstudio.com/DefaultCollection/Gangway/_versionControl | 2022-06-16 | 2022-07-01 | Completed/Testing Pending | Run time errors while testing | No | Dependendacy on common DLL's Dependency on few more services for testing application
4 |  | OPMS/SherlockAdmin | Asp.net MVC Web | High | C# + SP Migration |  | https://ccldev.visualstudio.com/DefaultCollection/Sherlock/_git/AdminTool | 2022-06-16 | 2022-07-01 | Completed/Testing Pending |  |  | Required Postman collection for migrated services for testing Dependendacy on common DLL's
40 |  | sherlockmanagementservice | API | High | C# + SP Migration | sherlockmanagementservice | https://ccldev.visualstudio.com/DefaultCollection/Sherlock/_versionControl?path=%24/Sherlock/Dev/SherlockManagementService | 2022-07-18 | 2022-07-29 | Completed/Testing Pending |  | Yes | Required Postman collection for migrated services for testing Dependendacy on common DLL's Dependency on few more services for testing application | Pre & post migration run need to be recorded
51 |  | CommonFramework | Library | High | Only C# Migration | CommonFramework (Workbook) | https://ccldev.visualstudio.com/DefaultCollection/StrategicServices/_versionControl?path=%24/StrategicServices/CommonFramework | 2022-06-16 |  | Inprogress |  |  | Complexity of error is more(around 130+ errors)
Authenticationservice
|  | Client.Common | Library |  |  |  | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/Client.Common | 2022-06-16 |  |  |  |  | Yet To start
|  | ConfigurationService | API | [6 empty] | Inprogress |  | Yes
|  | loginservice | API |  |  |  | https://ccldev.visualstudio.com/GuestTechStrategicServices/_git/Login |  |  | Inprogress |  |  | Yet To start
41 |  | sherlockwebservice | API | High | C# + SP Migration | sherlockwebservice | https://ccldev.visualstudio.com/DefaultCollection/StrategicServices/_versionControl?path=%24/StrategicServices/ImagingMediaWindow | 2022-07-18 | 2022-07-29 | Completed/Testing Pending |  | Yes | Required Postman collection for migrated services for testing Dependendacy on common DLL's
5 | api5a/5b | analyticsservice | API | Medium | Only C# Migration | analyticsservice | https://ccldev.visualstudio.com/DefaultCollection/GuestTechStrategicServices/_git/AnalyticsService | 2022-06-16 | 2022-07-01 | Completed/Testing Pending | Run time errors while testing | Yes | Dependendacy on common DLL's -Required Postman collection for migrated services for testing -Data first Model architecture need to be inplemented Dependency on Order service.
6 |  | applicationservice | API | Medium | C# + SP Migration | applicationservice | https://ccldev.visualstudio.com/DefaultCollection/GuestTechStrategicServices/_git/ShoreEx | 2022-06-16 | 2022-07-01 | Inprogress |  | Yes- ShoreEx | Required Postman collection for migrated services for testing Dependendacy on common DLL's Dependency on few more services for testing application
7 |  | Authenticationservice | API | High | Complete Rewrite | Authenticationservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/Authentication | Phase2 | Phase2 |  |  | Yes
8 |  | Authorizationservice | API | High | Complete Rewrite | Authorizationservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/Authorization | Phase2 | Phase2 |  |  | Yes
9 |  | businessservice | API | Medium | C# + SP Migration | businessservice | https://ccldev.visualstudio.com/DefaultCollection/GuestTechStrategicServices/_git/ShoreEx | 2022-06-16 | 2022-07-01 | Inprogress |  |  | Required Postman collection for migrated services for testing Dependendacy on common DLL's Dependency on few more services for testing application
10 |  | Configurationservice | API | High | Complete Rewrite | Configurationservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/ConfigurationService | 2022-06-16 | 2022-07-01
11 |  | contentservice | API | Medium | Only C# Migration | contentservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/Content | 2022-06-16 | 2022-07-01 | Inprogress |  | Yes | dependancy on orderproduct
12 |  | crewservice | API | Medium | C# + SP Migration | crewservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/Crew | 2022-06-16 | 2022-07-01 | Completed/Testing Pending |  | Yes | Required Postman collection for migrated services for testing -Data first Model architecture need to be inplemented Dependendacy on common DLL's Dependency on few more services for testing application
13 |  | datasynchronizationservice | API | Medium | C# + SP Migration | datasynchronizationservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/DataSynchronization | 2022-06-16 | 2022-07-01 | Inprogress |  |  | Required Postman collection for migrated services for testing Dependendacy on common DLL's Dependency on few more services for testing application
14 |  | deviceservice | API | Medium | C# + SP Migration | deviceservice | Yet To Receive Code
15 |  | exceptionconfigurationservice | API | Medium | Only C# Migration | exceptionconfigurationservice | https://ccldev.visualstudio.com/DefaultCollection/GuestTechStrategicServices/_git/ExceptionConfigurationService | 2022-07-04 | 2022-07-15 | Last Sprint
16 |  | externalsystemservice | API | Medium | Only C# Migration | externalsystemservice | https://ccldev.visualstudio.com/DefaultCollection/GuestTechStrategicServices/_git/ExternalSystemsService | 2022-07-04 | 2022-07-15
17 |  | notificationservice | API | Medium | Only C# Migration | notificationservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/NotificationService | 2022-07-04 | 2022-07-15 | Last Sprint
18 |  | orderproductservice | API | High | Only C# Migration | orderproductservice |  | 2022-07-04 | 2022-07-15 | Last Sprint
19 |  | productservice | API | Medium | C# + SP Migration | productservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/Product | 2022-07-04 | 2022-07-15 |  |  | Yes
20 |  | referencedataservice | API | Medium | C# + SP Migration | referencedataservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/ReferenceData | 2022-07-04 | 2022-07-15
21 |  | reportingservice | API | Medium | C# + SP Migration | reportingservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/Reporting | 2022-07-04 | 2022-07-15
22 |  | shiptimeservice | API | Low | C# + SP Migration | shiptimeservice |  | 2022-07-04 | 2022-07-15 |  |  | Yes
23 |  | shoreexprocess | API | Medium | Only C# Migration | shoreexprocess |  | 2022-07-04 | 2022-07-15
24 |  | targetedoffersservice | API | Medium | Only C# Migration | targetedoffersservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/TargetedOffersAPI | 2022-07-04 | 2022-07-15
25 | api4a/4b | darkroomprocessingwindowservice | Windows Service | High | C# + SP Migration | darkroomprocessingwindowservice | https://ccldev.visualstudio.com/DefaultCollection/Sherlock/_versionControl?path=%24/Sherlock/Dev/DarkRoomSimulator | 2022-07-04 | 2022-07-15
26 |  | embarkationstatisticsservice | API | Medium | C# + SP Migration | embarkationstatisticsservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/EmbarkationStatistics/ | 2022-07-04 | 2022-07-15
27 |  | guestservice | API | Medium | C# + SP Migration | guestservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/Guest | 2022-07-04 | 2022-07-15
28 |  | imagingmediaservice | API | High | C# + SP Migration | imagingmediaservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/ImagingMedia | 2022-07-04 | 2022-07-15
29 |  | personalertservice | API | Medium | C# + SP Migration | personalertservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/PersonAlert | 2022-07-04 | 2022-07-15
30 |  | personeventservice | API | Medium | C# + SP Migration | personeventservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/PersonEvent | 2022-07-04 | 2022-07-15
31 |  | personstatusservice | API | Medium | C# + SP Migration | personstatusservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/PersonStatus | 2022-07-04 | 2022-07-15
32 |  | reservationservice | API | High | C# + SP Migration | reservationservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/Reservation | 2022-07-04 | 2022-07-15
33 |  | shipservice | API | Medium | C# + SP Migration | shipservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/Ship | 2022-07-04 | 2022-07-15
34 |  | visitorservice | API | Medium | C# + SP Migration | visitorservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/Visitor | 2022-07-04 | 2022-07-15
35 |  | voyageservice | API | Medium | C# + SP Migration | voyageservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/Voyage | 2022-07-04 | 2022-07-15
36 | api2a/2b | capturedmediaservice | API | High | C# + SP Migration | capturedmediaservice | https://ccldev.visualstudio.com/StrategicServices/_versionControl?path=%24/StrategicServices/CapturedMedia | 2022-07-18 | 2022-07-29
37 |  | guestimagingservice | API | High | C# + SP Migration | guestimagingservice | https://ccldev.visualstudio.com/DefaultCollection/Sherlock/_versionControl?path=%24/Sherlock/Dev/GuestImagingService | 2022-07-18 | 2022-07-29
38 |  | guestreferencephotoservice | API | High | C# + SP Migration | guestreferencephotoservice | https://ccldev.visualstudio.com/DefaultCollection/Sherlock/_versionControl?path=%24/Sherlock/Dev/ReferencePhotoUploadUtility | 2022-07-18 | 2022-07-29
39 |  | loginservice | API | Medium | C# + SP Migration | loginservice |  | 2022-07-18 | 2022-07-29
42 | app4 | seams | Asp.net MVC Web | High | C# + SP Migration | seams web app | $/StrategicServices/Seams-Code/FHMACMS | 2022-07-18 | 2022-07-29
43 | svc1/svc2 | imagingwindowsservice | Windows Service | High | C# + SP Migration | imagingwindowsservice | https://ccldev.visualstudio.com/DefaultCollection/Sherlock/_versionControl?path=%24/Sherlock/Dev/ImageProcessingWindowsService | Phase2 | Phase2
44 |  | imageprocessingwindowsservice | Windows Service | High | C# + SP Migration | imageprocessingwindowsservice | https://ccldev.visualstudio.com/DefaultCollection/Sherlock/_versionControl?path=%24/Sherlock/Dev/ImageProcessingWindowsService | Phase2 | Phase2
45 |  | orderprocessingwindowsservice | Windows Service | High | C# + SP Migration | orderprocessingwindowsservice |  | Phase2 | Phase2
46 | dmzweb2 | seamsapi |  | Medium |  | seamsapi |  | 2022-07-18 | 2022-07-29
47 |  | weatherapi/Carnival.SeaMS.WeatherInfo | Library | Medium | C# + SP Migration | weatherapi |  | 2022-07-18 | 2022-07-29
48 |  | ShoreExCacheService | Windows Service | Medium | Only C# Migration | Shoreex Cache Service | https://ccldev.visualstudio.com/DefaultCollection/StrategicServices/_versionControl?path=%24/StrategicServices/ShoreEx/SitecoreCacheService | 2022-07-18 | 2022-07-29
49 |  | TurnStyle Middleware | API | Low | Only C# Migration | TurnStyleGateway | https://ccldev.visualstudio.com/DefaultCollection/Middleware/_git/TurnStyleMiddleware | 2022-07-18 | 2022-07-29
50 |  | Spa Cache Service | Windows Service | Medium | Only C# Migration | SpaCacheService | https://ccldev.visualstudio.com/DefaultCollection/StrategicServices/_versionControl?path=%24/StrategicServices/Spa/SitecoreCacheService | Phase2 | Phase2
|  | DataArchivalService | Windows Service | [5 empty] | Phase3
|  | ShipboardSynchronization Service | Windows Service | [5 empty] | Phase4
|  | Carnival.SeaMS.Replication.WindowsService | Windows Service
|  | Carnival.SeaMS.VoyageApi | Web Application | High |  | Seams Voyage | Seams-Code\Carnival.SeaMS.VoyageApi